One-Month TIMS Readout Plan

Prepared for Francesca | Start date: April 29, 2026 | Weekly touchpoint: Francesca, Khalid, and N

OBJECTIVE

I want to keep the next month focused. I would not add MEG into this first month, because that would add a separate lab, booking, acquisition setup, and analysis pipeline. The first step is simpler: show whether TIMS gives us a recoverable EEG response, and whether that response changes with stimulation intensity in a way that is comparable to the logic we use in TMS.

Success does not require every metric to work. The month is successful if one or two readouts are reliable enough to justify the next step: a TIMS-evoked potential, ITPC/PLV or coherence, resting-state power or delta stability, entropy, or cortical excitability before versus after stimulation.

PROTOCOL LOGIC

We start with the 100% theta-burst stimulation protocol on Khalid, focused on M1 first because it gives the clearest comparison point to TMS-EEG and MEP-based excitability. We recover the immediate event-related response, then test whether the signal is clean enough to interpret and not dominated by artifact.

In parallel, we run before/after readouts: resting-state EEG for power, delta stability, and entropy, plus sparse pulse stimulation to test whether cortical excitability changes after TIMS. If the 100% protocol gives a convincing signal, we move into dose-response testing at 100%, 50%, 25%, and 10% using the same acquisition and analysis logic.

EXPERIMENT STRUCTURE

| 1. 100% M1 TIMS Khalid; recover evoked response + before/after EEG | > | 2. Metric decision TEP first; otherwise ITPC/PLV, power, entropy, excitability | > | 3. Dose response Repeat at 100%, 50%, 25%, and 10% | > | 4. Replication Four additional participants; individual + group readout |
| --- | --- | --- | --- | --- | --- | --- |

MONTHLY LAYOUT

| Week | Key action | Deliverable | Main constraint | People |
| --- | --- | --- | --- | --- |
| Week 1 Apr 29-May 3 | Finalize the analysis pipeline, run the field/depth simulation from the core drive, and recover first TIMS-evoked responses from available data. | Short simulation output plus first EEG plots showing whether we can recover a clean response and phase-consistency metrics. | Pipeline sorting and true response versus stimulation artifact. | Khalid + N |
| Week 2 May 4-May 10 | Run the 100% M1 theta-burst protocol on Khalid and analyze immediate, resting-state, and excitability readouts. | First decision memo: best metric, whether the response is TMS-like enough to compare, and whether to move into dose response. | Not all metrics will be reliable; pivot to the strongest readout. | Khalid + N; Francesca review |
| Week 3 May 11-May 17 | Repeat the same protocol across 100%, 50%, 25%, and 10% stimulation intensity. | Preliminary dose-response trend across the strongest metrics: TIMS-evoked response, ITPC/PLV/coherence, power/entropy, or excitability. | Order effects, fatigue, and keeping the protocol identical. | Khalid + N |
| Week 4 May 18-May 24 | Replicate the most promising protocol in four additional participants or patients. | Individual plots plus a first group-average summary showing whether the effect replicates beyond N=1. | Scheduling and inter-individual variability. | Khalid + N; Francesca unblockers |

DECISION RULE

By the end of Week 2, we choose the metric that carries the project forward. If we have a clean TIMS-evoked potential, that becomes the anchor. If not, we move with the strongest reliable alternative: phase consistency, resting-state power or delta stability, entropy, or cortical excitability. By the end of Week 4, the deliverable is a concise result package showing whether TIMS has a plausible physiological effect, whether it scales with intensity, and whether it replicates across participants.

Metric language is aligned with standard TMS-EEG readouts: evoked potentials, GMFA/GMFP, time-frequency measures, phase consistency, and artifact constraints; plus recent descriptions of ITPC and canonical TEP windows.